Work Plan

Friday, 27th of February 2015

2IO70

The purpose of this document is to help understand and organise the process of our project, by defining the concepts, tasks, subtasks, responsibilities, and deadlines. This document describes how we are going to manage our time to complete the project.

Group 16
Verschuuren R.T. (Rolf)
Keet M. (Maarten)
Phung D.T. (Dat)
Version 3.0

## Defining our terms
Wp	= Work Plan
Df	= Defining our terms
Tt	= Create weekly timetables
Md	= Machine Design
Mi	= Machine Interface
Tc	= Defining Test cases
L	= Compiling and defining layout of the document
Cr	= Cross-reading
Ss	= Software Specification
In	= Inputs
Ot	= Outputs
Dio	= Dependence of outputs on inputs
Ias	= Inventory of abstract states
Sc	= State changes depending on inputs
UPP	= Create an UPPAAL model of the machine
L	= Compiling and defining layout of the document
Cr	= Cross-reading
Sd	= Software Design
I/o	= Pick variables for In/Out registers
Fe	= Formulate Exception Service Routines
Ec	= Explain the correctness of our program
Dd	= Motivate design decisions
L	= Compiling and defining layout of the document
Cr	= Cross-reading
Si	= Software Implementation and Integration
Cs	= Develop coding standards / Document the compiler
Fa	= Debug the Assembly program
L	= Compiling and defining layout of the document
Cr	= Cross-reading
VaT	= Validation and Testing
Tc	= Evaluate test cases / Perform test cases
SLR	= Check whether SLRs are met
Uf	= Check unintended functionality
Dv	= Define how part of the process is going to be validated
Co	= Code review
Pr	= Make formal proofs
L	= Compiling and defining layout of the document
Cr	= Cross-reading
FR	= Final Report
L	= Compiling and defining layout of the document
Cr	= Cross-reading
Pr	= Presentation
Mp	= Making presentation
P	= Practicing

P	=President
S	=Secretary
Q	=Quality assurance manager
M	=Materials manager
## Total work
Project	Week 4	Week 5	Week 6	Week 7	Week 8	Total
Wp	20					20
Md	20					20
Ss	45	90				135
Sd			90	10		100
Si				60		60
Vat	17	12	12	32	12	85
FR					54	45
Pr					24	45
Total	102	102	102	102	90	500

Deliverables
Project	Responsibility	Deadline
Work Plan	Rolf	March 3, 2015
Machine Design	Maarten	March 3, 2015
Software Specification	Rolf	March 13, 2015
Software Design	Wigger	March 27, 2015
Software Implementation and Integration	Stefan	March 27, 2015
Validation and Testing	Tudor	April 3, 2015
Final Report	Dat	April 17, 2015

## Week 4
Tuesday
Time	Wigger	Stefan	Rolf	Dat (Q)	Maarten (P) (M)	Tudor (S)
1030-1100	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1100-1130	Md.mi	Md.mi	Wp	Wp	Wp	Md.tc
1130-1230	Md.mi	Md.mi	Wp	Wp	Wp	Md.tc
1230-1330	Md.mi	Md.mi	Wp	Wp	Wp	Md.tc
1330-1430		Wp		Wp		Md.tc
1430-1530	Md.l	Wp	Wp	Wp	Wp	Md.tc
1530-1630		Wp	Wp	Wp	Wp	Md.tc
1630-1730

Wednesday
Time	Wigger	Stefan	Rolf	Dat (Q)	Maarten (P) (M)	Tudor (S)
1230-1330	Ss.In	Ss.In	Ss.Ot	Ss.Ot	Ss.Ot	Md.tc
1330-1430	Ss.In	Ss.In	Ss.Ot	Ss.Ot	Ss.Ot	Md.tc
1430-1530	Ss.In	Ss.In	Ss.Ot	Ss.Ot	Ss.Ot	Md.tc
1530-1630	Md.l	Ss.In	Ss.Ot	Ss.Ot	Ss.Ot	Ss.in
1630-1730	Md.l	Ss.In	Ss.Ot	Ss.Ot	Ss.Ot	Ss.in

Friday
Time	Wigger	Stefan	Rolf	Dat (Q)	Maarten (P) (M)	Tudor (S)
1030-1130	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1130-1230	Ss.dio	Ss.dio	Ss.ias	Ss.ias	Ss.ias	Ss.dio
1230-1330	Ss.dio	Ss.dio	Ss.ias	Ss.ias	Ss.ias	Ss.dio
1330-1430	Ss.dio	Ss.dio	Ss.ias	Ss.ias	Ss.ias	Ss.dio
1430-1530	Ss.dio	Ss.dio	Ss.sc	Ss.sc	Ss.sc	Ss.dio
1530-1630	Ss.cr	Ss.cr	Ss.sc	Ss.sc	Ss.sc	Ss.cr
1630-1730	Ss.cr	Ss.cr	Ss.cr	Ss.cr	Ss.cr	Ss.cr

## Week 5
Tuesday
Time	Wigger	Stefan (S)	Rolf	Dat (Q)	Maarten (M)	Tudor (P)
1030-1100	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1100-1130	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1130-1230	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1230-1330	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1330-1430	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1430-1530	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1530-1630	VaT	VaT	VaT	VaT	VaT	VaT

Wednesday
Time	Wigger	Stefan (S)	Rolf	Dat (Q)	Maarten (M)	Tudor (P)
1230-1330	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1330-1430	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1430-1530	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1530-1630	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1630-1730	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp

Friday
Time	Wigger	Stefan (S)	Rolf	Dat (Q)	Maarten (M)	Tudor (P)
1030-1130	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1130-1230	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp	Ss.Upp
1230-1330	Ss.Cr	Ss.Cr	Ss.Cr	Ss.L	Ss.Cr	Ss.Cr
1330-1430	Ss.Cr	Ss.Cr	Ss.Cr	Ss.L	Ss.Cr	Ss.Cr
1430-1530	Ss.Cr	Ss.Cr	Ss.Cr	Ss.L	Ss.Cr	Ss.Cr
1530-1630	VaT	VaT	VaT	VaT	VaT	VaT

## Week 6
Tuesday
Time	Wigger	Stefan (P)	Rolf	Dat (S) (Q)	Maarten (M)	Tudor
1030-1100	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1100-1130	Sd.I/o	Sd.I/o	Sd.I/o	Sd.I/o	Sd.I/o	Sd.I/o
1130-1230	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1230-1330	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1330-1430	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1430-1530	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1530-1630	VaT.Co	VaT.Co	VaT.Co	VaT.Co	VaT.Co	VaT.Co

Wednesday
Time	Wigger	Stefan (P)	Rolf	Dat (S) (Q)	Maarten (M)	Tudor
1230-1330	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1330-1430	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1430-1530	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe	Sd.Fe
1530-1630	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec
1630-1730	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec	Sd.Ec

Friday
Time	Wigger	Stefan (P)	Rolf	Dat (S) (Q)	Maarten (M)	Tudor
1030-1130	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1130-1230	Sd.Ec	Sd.Ec	Sd.L	Sd.Ec	Sd.Ec	Sd.Ec
1230-1330	Sd.Dd	Sd.Dd	Sd.L	Sd.Dd	Sd.Dd	Sd.Dd
1330-1430	Sd.Dd	Sd.Dd	Sd.L	Sd.Dd	Sd.Dd	Sd.Dd
1430-1530	Sd.Dd	Sd.Dd	Sd.L	Sd.Dd	Sd.Dd	Sd.Dd
1530-1630	VaT.Co	VaT.Co	VaT.Co	VaT.Co	VaT.Co	VaT.Co

## Week 7
Tuesday
Time	Wigger (P)	Stefan (S)	Rolf	Dat	Maarten (Q) (M)	Tudor
1030-1100	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1100-1130	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr
1130-1230	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr	Sd.Cr
1230-1330	Sd.Cr	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs
1330-1430	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs
1430-1530	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs
1530-1630	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs

Wednesday
Time	Wigger (P)	Stefan (S)	Rolf	Dat	Maarten (Q) (M)	Tudor
1230-1330	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs	Si.Cs
1330-1430	Si.Cs	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.Fa
1430-1530	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.Fa
1530-1630	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.Fa
1630-1730	Si.Fa	Si.Fa	Si.Fa	Si.Fa	Si.L	Si.Cr

Friday
Time	Wigger (P)	Stefan (S)	Rolf	Dat	Maarten (Q) (M)	Tudor
1030-1130	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1130-1230	Si.Cr	Si.Cr	Si.Cr	Vat.Pr	Vat.Pr	Vat.Pr
1230-1330	Vat.Pr	Vat.Pr	Vat.Pr	Vat.Pr	Vat.Pr	Vat.Pr
1330-1430	Vat.Pr	Vat.L	Vat.L	Vat.L	Vat.L	Vat.L
1430-1530	Vat.L	Vat.L	Vat.L	Vat.L	Vat.L	Vat.Cr
1530-1630	Vat.Cr	Vat.Cr	Vat.Cr	Vat.Cr	Vat.Cr	Vat.Cr

## Week 8
Tuesday
Time	Wigger	Stefan	Rolf (P)	Dat	Maarten (S) (Q) (M)	Tudor
1030-1100	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1100-1130	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1130-1230	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1230-1330	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1330-1430	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1430-1530	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1530-1630	VaT.L	VaT.L	VaT.L	VaT.L	VaT.L	VaT.L

Wednesday
Time	Wigger	Stefan	Rolf (P)	Dat	Maarten (S) (Q) (M)	Tudor
1230-1330	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp
1330-1430	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp
1430-1530	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp	Pr.Mp
1530-1630	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L
1630-1730	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L	Fr.L

Friday
Time	Wigger	Stefan	Rolf (P)	Dat	Maarten (S) (Q) (M)	Tudor
1030-1130	Meeting	Meeting	Meeting	Meeting	Meeting	Meeting
1130-1230	Pr.P	Pr.P	Pr.P	VaT.Cr	VaT.Cr	VaT.Cr
1230-1330	Pr.P	Pr.P	Pr.P	VaT.Cr	VaT.Cr	VaT.Cr
1330-1430	Pr.P	Pr.P	Pr.P	VaT.Cr	VaT.Cr	VaT.Cr
1430-1530
1530-1630

Validation
We validate the work plan by comparing the expected time it would take to finish each task in the schedule with the time spent working on the corresponding task in the collective logbook. The logbook serves as an indication of how much time was spent on a certain task by each member of the group.

Change policy and conclusions
Suppose that some unforeseen problems arise and it’s going to be nearly impossible to meet a deadline. Unfortunately, then we will all have to spend more time on a subtask. Should there be a significant difference between the schedule and the logbook, then it is expected that the member of the group does their work at home.