## Sheet1
Machine Design
Task | Responsible | Done when | Duration
Finishing document | Maarten | 6th of March | 1 | 2.1254
Defining test cases | Tudor |  | 4 | 8.5016
Interface part document | Wigger and Stefan |  | 4 | 8.5016
Adjusting document according to feedback | Rolf |  | 2 | 4.2508
Ensure result of phase is specification for next phase |  |  | 1 | 2.1254
Cross reading |  |  | 1.5 | 3.1881
Software Specification |  |  |  | 0
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Rolf | 10th of March | 1 | 2.1254
Document inputs |  |  | 1.5 | 3.1881
Document outputs |  |  | 2 | 4.2508
Dependence outputs-inputs |  |  | 1 | 2.1254
Create inventory of abstract states |  |  | 1 | 2.1254
State changes depending on input |  |  | 1 | 2.1254
Prepare UPPAAL |  |  | 4 | 8.5016
Create UPPAAL model |  |  | 5 | 10.627
Defining purpose |  |  | 0.5 | 1.0627
Ensure result of phase is specification for next phase |  |  | 1 | 2.1254
Cross reading |  |  | 1.5 | 3.1881
Software Design |  |  |  | 0
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Wigger |  | 1 | 2.1254
Formulate ESRs |  |  | 3 | 6.3762
Represent I/O registers |  |  | 1 | 2.1254
Explain correctness |  |  | 6 | 12.7524
Motivation design decisions |  |  | 3 | 6.3762
Defining purpose |  |  | 0.5 | 1.0627
Ensure result of phase is specification for next phase |  |  | 1 | 2.1254
Cross reading |  |  | 1.5 | 3.1881
Software Implementation & Integration |  |  |  | 0
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Stefan |  | 1 | 2.1254
Develop coding standards |  |  | 4 | 8.5016
Documentation coding standards |  |  | 3 | 6.3762
Documentation data representation chosen |  |  | 2 | 4.2508
Defining purpose |  |  | 0.5 | 1.0627
Integration and testing |  |  | 6 | 12.7524
Finishing Assembly program |  |  | 1 | 2.1254
Ensure result of phase is specification for next phase |  |  | 1 | 2.1254
Cross reading |  |  | 1.5 | 3.1881
System Validation and Testing |  |  |  | 0
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Tudor |  | 2 | 4.2508
Defining purpose |  |  | 0.5 | 1.0627
Evaluate test cases |  |  | 8 | 17.0032
Check if SLRs are met |  |  | 4 | 8.5016
Cross reading |  |  | 4 | 8.5016
Check unintended functionality |  |  | 3 | 6.3762
Define how certain parts of the machine are going to be validated (code review, test cases or formal proofs) |  |  | 3.5 | 7.4389
Do the code review |  |  | 22 | 46.7588
Perform test cases |  |  | 5 | 10.627
Make formal proofs |  |  | 7 | 14.8778
Define how to do the code review (walkthrough, formal peer review, pair programming) |  |  | 4 | 8.5016
Walkthrough |  |  | 12 | 25.5048
Formal peer review |  |  | 8 | 17.0032
Pair programming |  |  | 12 | 25.5048
“Review report” |  |  | 10 | 21.254
Write final verdict on test runs |  |  | 2 | 4.2508
Statement coverage |  |  | 3 | 6.3762
Condition coverage |  |  | 5 | 10.627
Decision coverage |  |  | 4 | 8.5016
Modified condition/decision coverage |  |  | 8 | 17.0032
Test case executions documentation |  |  | 4 | 8.5016
Documentation formal proofs |  |  | 8 | 17.0032
Completion |  |  |  | 0
Task | Responsible | When done | Duration | #VALUE!
Finishing Final Report | Dat |  | 3 | 6.3762
Document Introduction |  |  | 0.5 | 1.0627
Document Conclusion |  |  | 1 | 2.1254
Documenting purpose |  |  | 0.5 | 1.0627
Document method working |  |  | 1 | 2.1254
Document Specification |  |  | 3 | 6.3762
Document Validation |  |  | 4 | 8.5016
Document Design of software |  |  | 4 | 8.5016
Motivate main design decisions |  |  | 2 | 4.2508
Presentation and demonstration |  |  |  | 0
Task | Responsible | When done | Duration | #VALUE!
Preparation | Wigger, Rolf, Stefan |  | 5 | 10.627
Presentation | Wigger, Rolf and Stefan |  | 0.25 | 0.53135
Demonstration |  |  | 0.5 | 1.0627
Reflection |  |  |  | 0
Task | Responsible | When done | Duration | #VALUE!
Reflection |  |  | 1.5 | 3.1881
235.25