## Sheet1
Machine Design
Task | Responsible | Done when | Duration
Finishing document | Maarten | 6th of March | 1 | 1.4815
Defining test cases | Tudor |  | 4 | 5.9259
Interface part document | Wigger and Stefan |  | 4 | 5.9259
Adjusting document according to feedback | Rolf |  | 2 | 2.963
Ensure result of phase is specification for next phase |  |  | 1 | 1.4815
Cross reading |  |  | 1.5 | 2.2222
Software Specification |  |  | 13.5 | 20
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Rolf | 10th of March | 1 | 6.9231
Document inputs |  |  | 1.5 | 10.3846
Document outputs |  |  | 2 | 13.8462
Dependence outputs-inputs |  |  | 1 | 6.9231
Create inventory of abstract states |  |  | 1 | 6.9231
State changes depending on input |  |  | 1 | 6.9231
Prepare UPPAAL |  |  | 4 | 27.6923
Create UPPAAL model |  |  | 5 | 34.6154
Defining purpose |  |  | 0.5 | 3.4615
Ensure result of phase is specification for next phase |  |  | 1 | 6.9231
Cross reading |  |  | 1.5 | 10.3846
Software Design |  |  | 19.5 | 135
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Wigger |  | 1 | 5.8824 | Cr
Formulate ESRs |  |  | 3 | 17.6471 | Fe
Represent I/O registers |  |  | 1 | 5.8824 | I/o
Explain correctness |  |  | 6 | 35.2941 | Ec
Motivation design decisions |  |  | 3 | 17.6471 | Dd
Defining purpose |  |  | 0.5 | 2.9412 | L
Ensure result of phase is specification for next phase |  |  | 1 | 5.8824 | Cr
Cross reading |  |  | 1.5 | 8.8235 | Cr
Software Implementation & Integration |  |  | 17 | 100
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Stefan |  | 1 | 3 | Cr
Develop coding standards |  |  | 4 | 12 | Cs
Documentation coding standards |  |  | 3 | 9 | Cs
Documentation data representation chosen |  |  | 2 | 6 | Cs
Defining purpose |  |  | 0.5 | 1.5 | L
Integration and testing |  |  | 6 | 18 | Fa
Finishing Assembly program |  |  | 1 | 3 | Fa
Ensure result of phase is specification for next phase |  |  | 1 | 3 | Cr
Cross reading |  |  | 1.5 | 4.5 | Cr
System Validation and Testing |  |  | 20 | 60
Task | Responsible | Done when | Duration | #VALUE!
Finishing document | Tudor |  | 2 | 1.0791
Defining purpose |  |  | 0.5 | 0.26978
Evaluate test cases |  |  | 8 | 4.3165
Check if SLRs are met |  |  | 4 | 2.1583
Cross reading |  |  | 4 | 2.1583
Check unintended functionality |  |  | 3 | 1.6187
Define how certain parts of the machine are going to be validated (code review, test cases or formal proofs) |  |  | 3.5 | 1.8885
Do the code review |  |  | 22 | 11.8705
Perform test cases |  |  | 5 | 2.6978
Make formal proofs |  |  | 7 | 3.777
Define how to do the code review (walkthrough, formal peer review, pair programming) |  |  | 4 | 2.1583
Walkthrough |  |  | 12 | 6.4748
Formal peer review |  |  | 8 | 4.3165
Pair programming |  |  | 12 | 6.4748
“Review report” |  |  | 10 | 5.3957
Write final verdict on test runs |  |  | 2 | 1.0791
Statement coverage |  |  | 3 | 1.6187
Condition coverage |  |  | 5 | 2.6978
Decision coverage |  |  | 4 | 2.1583
Modified condition/decision coverage |  |  | 8 | 4.3165
Test case executions documentation |  |  | 4 | 2.1583
Documentation formal proofs |  |  | 8 | 4.3165
Completion |  |  | 139 | 75
Task | Responsible | When done | Duration | #VALUE!
Finishing Final Report | Dat |  | 3 | 7.1053
Document Introduction |  |  | 0.5 | 1.1842
Document Conclusion |  |  | 1 | 2.3684
Documenting purpose |  |  | 0.5 | 1.1842
Document method working |  |  | 1 | 2.3684
Document Specification |  |  | 3 | 7.1053
Document Validation |  |  | 4 | 9.4737
Document Design of software |  |  | 4 | 9.4737
Motivate main design decisions |  |  | 2 | 4.7368
Presentation and demonstration |  |  | 19 | 45
Task | Responsible | When done | Duration | #VALUE!
Preparation | Wigger, Rolf, Stefan |  | 5 | 31.0345
Presentation | Wigger, Rolf and Stefan |  | 0.25 | 1.5517
Demonstration |  |  | 0.5 | 3.1034
Reflection |  |  |  | 35.6897
Task | Responsible | When done | Duration | #VALUE!
Reflection |  |  | 1.5 | 9.3103
|  |  | 7.25 | 45 | Sum
515.6897